## Team
Initials | First | Last | Email | GitHub Username
ja | Joseph | Allen | jallen2@stevens.edu | jallenNJ
ykh | Yikun | Han | yhan34@stevens.edu | yklhan
dah | Deborah | Harrington | dharring@stevens.edu | daharrington1
cz | Chengyi | Zhang | czhan9@stevens.edu | MarquisBan
|  |  | GitHub Repository: | https://github.com/daharrington1/CS555W.git
Group Dynamics:
- Programming Language |  |  | Python3
- Dependencies |  |  | pymongo, nltk, tabulate, punkt
- Database |  |  | MongoDB
- Communication: Emai & Discusson Board Zoom meetings: Mon/Thurs at 8:00PM ET.
- Team Member Roles
Joseph Allen: GitHub Merge Administrator Developer, Tester
Yikun Han: Developer, Tester
Debbie Harrington: Scrum Master, Developer, Tester
Changyi Zhang: Developer, Tester

## Backlog
Sprint | Story ID | Story Name | Owner | Status | Story Points | Priority
1 | US01 | Dates before current date | ykh | Completed | 1 | 1
1 | US07 | Less then 150 years old | ykh | Completed | 1 | 1
1 | US17 | No Marriages to Children | dah | Completed | 2 | 1
1 | US18 | Siblings should not marry | dah | Completed | 2 | 1
1 | US29 | List Deceased | ja | Completed | 1 | 1
1 | US23 | Unique name and birth date | ja | Completed | 1 | 1
1 | US24 | Unique families by spouses | cz | Completed | 1 | 1
1 | US32 | List multiple births | cz | Completed | 1 | 1
2 | US02 | Birth before marriage | ykh | Completed | 1 | 2
2 | US03 | Birth before death | ykh | Completed | 1 | 2
2 | US30 | List living married | dah | Completed | 2 | 2
2 | US31 | List living single | dah | Completed | 2 | 2
2 | US42 | Reject illegitimate dates | ja | Completed | 2 | 2
2 | US33 | List orphans | ja | Completed | 2 | 2
2 | US38 | List upcoming birthdays | cz | Completed | 2 | 2
2 | US11 | No bigamy | cz | Completed | 2 | 2
3 | US04 | Marriage before divorce | ykh |  | 1 | 3
3 | US05 | Marriage before death | ykh |  | 1 | 3
3 | US16 | Male last names | dah |  | 2 | 1
3 | US39 | List upcoming anniversaries | dah |  | 3 | 3
3 | US21 | Correct gender for role | ja |  | 2 | 3
3 | US13 | Siblings spacing | ja |  | 3 | 3
3 | US12 | Parents not too old | cz |  | 2 | 3
3 | US19 | First cousins should not marry | cz |  | 2 | 3
4 | US06 | Divorce before death | ykh |  | 1 | 4
4 | US10 | Marriage after 14 | ykh |  | 1 | 4
4 | US27 | Include individual ages | dah |  | 1 | 4
4 | US15 | There should be fewer than 15 siblings in a family | dah |  | 1 | 4
4 | US35 | List recent births | ja |  | 3 | 4
4 | US28 | Order siblings by age | ja |  | 2 | 4
4 | US34 | List large age differences | cz |  | 2 | 4
4 | US36 | List recent deaths | cz |  | 1 | 4

## Burndown README
The goal of the burndown chart is to help the agile team and customer to understand how the developers are doing
to deliver the product. Burndown charts can be done daily, weekly, at the end of a sprint, or at whatever time interval makes sense.
We'll update our burndown chart for the GEDCOM project at the end of each sprint.
At the end of each sprint, you should update the number of remaining stories, the LOC written to implement the user stories
implemented in this sprint, and the minutes needed to write those lines of code.
Here's a sample burndown chart for a team of three:
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2016-06-06 | 32 |  | 0
Sprint 1 | 6/19/2016 | 24 | 8 | 250 | 120 | 125
Sprint 2 | 2016-03-07 | 16 | 8 | 480 | 135 | 102.2
Sprint 3 | 7/17/2016 | 8 | 8 | 740 | 160 | 97.5
Sprint 4 | 7/31/2016 | 0 | 8 | 1100 | 145 | 149
= # team members * 4 sprints *
2 stories per sprint
lines of code per hour is calcuated by Excel
Velocity of completing user stories (calculated)
Total
LOC
How long to implement the user stories in this sprint
When we expect to complete all user stories

## Burndown
Sprint 1 | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2020-01-06 | 32 | 32 | 0 | 0
Sprint 1 | 2020-08-06 | 32 | 0 | 0 | 0
Sprint 1 | 6/20 | 24 | 8 | 427 | 750 | 34.16
Sprint2 | 2020-05-07 | 16 | 8 | 783 | 665 | 32.1203
Sprint3 | 7/19
Sprint4 | 2020-02-08

## Sprint1
| Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Source File | Source Function | Source Lines | Test File | Test Function | Test lines
US17 | No Marriages to children | dah | Completed | 50 | 120 | 164 | 380 | X | UserStory17.py, Main.py | us17_no_marr2childa, | 1-34 | US17Test .py | test* | 1-145
T17.01 | Write Tests | dah | Completed |  |  | 98 | 150 | X |  |  |  | US17Test.py | test* | 1-145
T17.02 | Write Method | dah | Completed |  |  | 66 | 230 | X | UserStory17.py, Utils.py, Main.py | us17_no_marr2childa, getParent2ChildrenMap, getMySpouse, getSpousesInFamily, | 1-34 38-72 75-102 105-128
US18 | Siblings Should not marry | dah | Completed | 50 | 30 | 104 | 60 | X | UserStory18.py, Main.py | us18_no_siblingmarriages, | 1-38 | US18Test.py | test* | 1-132
T18.01 | Write Test | dah | Completed |  |  | 91 | 40 | X |  |  |  | US18Test.py | test* | 1-132
T18.02 | Write Method | dah | Completed |  |  | 13 | 20 | X | UserStory18.py, Main.py | us18_no_siblingmarriages | 130-162
US29 | List Deceased | ja | Complete | 10 | 60 | 9 | 15 | X | main.py | __main__ |  | - | - | 31
T29.01 | Retrieve all Individuals that are deceased | ja | Complete | 9 | 50 | 5 | 10 | X | db_interface.py | getDeadAsList |  | DBinterfaceTest.py | test_get_dead_as_list ¦ test_no_dead_return_empty_list | 31
T29.02 | List Records of all the deceased | ja | Complete | 1 | 10 | 4 | 5 | X | TablePrinter.py | print_individuals |  | N/a | None, calls print() on unit tested functions | 0
US23 | Unique name and birth date | ja | Completed | 35 | 85 | 25 | 90 | X | Utils.py | filter_non_unique_individuals |  | UtilTest.py and TablePrinterTest.py | testValidDateMapping ¦ testInvalidSyntaxDateMappings ¦ test_filtering_non_uniques_on_non_unique_input ¦ test_filtering_non_uniques_on_unique_input ¦ test_filtering_non_uniques_on_malformed_key_input_raises | 100
US01 | Dates before current date | ykh | Completed | 15 | 60 | 37 | 80 | X | parseV4.py | dateCheck | 235-274 | project4test.py | test_dateTrav | 23-32
T01.01 | Get current date
T01.02 | Compare with the date
US07 | Less then 150 years old | ykh | Completed | 15 | 60 | 18 | 30 | X | parseV4.py | add_valid_age | 175-215 | project4test.py | test_age | 35-37
T07.01 | Compare current date with death date
T07.02 | Compare death date with 150+birthday
US24 | Unique families by spouses | cz | Completed | 30 | 45 | 45 | 45 | X | usrun.py | unique_family | 7-53 | usrun_test.py | test_uf | 72-88
T24.01 | Create an ID to individual dict | cz | Completed | 1 | 5 | 1 | 5 | X
T24.02 | Create a dict keyword by marriage date and value by spouses names | cz | Completed | 1 | 5 | 1 | 5 | X
T24.03 | Retrieve all families, add all families into the dict | cz | Completed | 10 | 5 | 10 | 5 | X
T24.04 | If there are more than 1 group of spouses, compare the names of each spouse to each other on this marriage date | cz | Completed | 30 | 30 | 30 | 30 | X
US32 | List multiple births | cz | Completed | 30 | 60 | 25 | 50 | X | usrun.py | multiple_births | 57-79 | usrun_test.py | test_mb | 93-107
T32.01 | Create a dict keyword by individual ID and value by birthdays | cz | Completed
T32.02 | Retrieve all individuals, add them into the dict | cz | Completed
T32.03 | If there are more than 1 birthdays in one's ID, print | cz | Completed
Business Purpose: to implement approximately 25% of highest priority validity checks and enhancement features defined for the current release.
Definition of Done: user story is fully implemented and submitted to github along with a corresponding test to prove the functionality of the check/feature.
| Review Results: | Two output files are in the zip file. The output when running the program Main.py on the input .ged file (ModernFamilyTest.ged) At least one example of each user case in this sprint displays information. The other output file shows the execution of all the unit tests in GroupGedcomTest. All implemented stories for this sprint are working correctly per customer requirements.
Retrospective:
What went well:
- Got all the stories done for the first sprint - Communication between team members went great. - Operational excellence among all team members - Pair Programming went great. Improved efficiency
What could improve:
- Reduce introducing errors into the Gedcom Test File when making changes - Optimize structure of Unit Test Directory - Common Naming/Structural Standards for coding, etc.

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Source File | Source Function | Source Lines | Test File | Test Function | Test lines
US30 | List living married | dah | Completed | 150 | 120 | 125 | 300 | X | UserStory30.py, Main.py | us30_get_married_individuals | 118-123 | US30Test .py | US30Test
T30.01 | Write Tests | dah | Completed |  |  |  |  | X |  |  |  | US30Test.py | US30Test | 1-455
T30.02 | Write Methods | dah | Completed |  |  | 94 | 80 | X | Utils.py, UserStory30.py, Main.py | getMaritalStatus (and many sub methods) us30_get_married_individuals | 51-281 1-26
T30.03 | Implement Continuous Integration | dah | Completed |  |  | 31 | 120 | X | python-app.yml | python-app.yml | 1-53
T30.04 | Refactoring | dah | Completed |  |  | N/A | 100 | X | Utils.py | US30/US31 methods in Utils | 51-281 | US30Test.py US31Test.py | US30Test US31Test | all
US31 | List living single | dah | Completed | 150 | 120 | 12 | 15 | X | UserStory31.py, Main.py | us31_get_single_individuals | 125-130 | US31Test.py | US31Test
T31.01 | Write Tests | dah | Completed |  |  |  |  | X |  |  |  | US31Test.py | US31Test | 1-440
T31.02 | Write Methods | dah | Completed |  |  | 12 | 15 | X | UserStory31.py, Main.py | us31_get_single_individuals | 1-27
US02 | Birth before marriage | ykh | completed | 30 | 60 | 26 | 90 | X | parser_checker.py | date_check | 281-306 | parserTest.py | test_dataTrav | 32,28
T02.01 | refactoring | [8 empty] | compTwoDate, us01_currentDate | 219-233
T02.02 | get birthday and marry day
T02.03 | compare these two dates
US03 | Birth before death | ykh | completed | 30 | 60 | 8 | 30 | X | parser_checker.py | date_check | 264-271 | parserTest.py | test_dataTrav | 29,33
T03.01 | get birthday and death day
T03.02 | compare these two dates
US42 | Reject illegitimate dates | ja | Completed | 25 | 75 | 55 | 30 | X | DateValidator.py | validate_date |  | DateValidatorTest.py | est_is_leap_year, test_valid_dates, test_invalid_dates | 65
US33 | List orphans | ja | Completed | 10 | 30 | 50 | 40 | X | UserStory33.py, Utils.Py, Main.py | find_all_orphans, all_spouses_dead, younger_than, normalize_spouse_ids | 1-33 | US33Test.py | test_younger_than_valid_data, test_younger_than_invalid_data, test_all_dead, test_find_orphans, test_find_orphans_no_results | 60
US38 | List upcoming birthdays | cz | Completed | 30 | 60 | 20 | 40 | X | us_run.py | upcoming_birthdays | 95-114 | usrun_test.py | test_ub | 30
T38.01 | Retrieve all individuals |  | Completed | 5 | 5 | 5 | 10 | X
T38.02 | Check if one's birthday is upcoming in 30 days |  | Completed | 20 | 40 | 15 | 30 | X
US11 | No bigamy | cz | Completed | 100 | 100 | 60 | 120 | X | us_run.py | no_bigamy_one_fam, no_bigamy_sev_fam | 117-177 | usrun_test.py | test_nb1, test_nbs | 60
T11.01 | First check if there are more than 2 spouses in any family |  | Completed
T11.02 | Retrieve all individuals |  | Completed
T11.03 | Retrieve all families of any individuals in which he/she is spouse |  | Completed
T11.04 | Retrieve all marriage date of these families |  | Completed
T11.05 | Retrieve all death dates of his/her spouse |  | Completed
T11.06 | Check if he/she marry when having a spouse alive |  | Completed
Business Purpose: to implement approximately 25% of highest priority validity checks and enhancement features defined for the current release.
Definition of Done: user story is fully implemented and submitted to github along with a corresponding test to prove the functionality of the check/feature.
Review Results: | Two output files are in the zip file. The output when running the program Main.py on the input .ged file (ModernFamilyTest.ged) At least one example of each user case in this sprint displays information. The other output file shows the execution of all the unit tests in GroupGedcomTest. All implemented stories for this sprint are working correctly per customer requirements.
Retrospective:
What went well:
- Got all the stories done for the second sprint - Added Continuous Integration to this Sprint for every commit - Reduced Flake8 warnings significantly - Communication between team members went great. - Operational excellence among all team members
What could improve:
- Maintaining one test file for running the Main Program - More Refactoring on the code - Continue Working towards Common Naming/Structural Standards for coding, etc.
Business Purpose: to implement approximately 25% of highest priority validity checks and enhancement features defined for the current release.
Definition of Done: user story is fully implemented and submitted to github along with a corresponding test to prove the functionality of the check/feature.
Review Results: | Two output files are in the zip file. The output when running the program Main.py on the input .ged file (ModernFamilyTest.ged) At least one example of each user case in this sprint displays information. The other output file shows the execution of all the unit tests in GroupGedcomTest. All implemented stories for this sprint are working correctly per customer requirements.
Retrospective:
What went well:
- Got all the stories done for the second sprint - Added Continous Integration to the Github Repo on all commits - Operational excellence among all team members
What could improve:
- Refactoring - lots of repeated code - Need to Clean Up Lint Problems - Continue to sync on common coding standards

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Source File | Source Function | Source Lines | Test File | Test Function | Test lines
US04 | marriage before divorce | ykh | not started | 10 | 30 |  |  |  | parser_checker.py | date_check |  | parserTest.py | test_dataTrav
T04.01 | get divorce day and marry day
T04.02 | compare these two dates
US05 | marriage before death | ykh | not started | 30 | 60 |  |  |  | parser_checker.py | date_check |  | parserTest.py | test_dataTrav
T05.01 | get marriage day and death day
T05.02 | compare these two dates
US21 | Correct gender for role | ja | Not started | 25 | 45 |  |  |  | TBD | TBD |  | TBD | TBD
US13 | Siblings spacing | ja | Not Started | 50 | 45 |  |  |  | TBD | TBD |  | TBD | TBD
US16 | Male last names | dah | In Progress | 40 | 60 |  |  |  | UserStory16.py, Main.py |  |  | US16Test.py | US16Test
T16.01 | Write Test Script | dah
T16.02 | Write Method | dah
US39 | List upcoming anniversaries | dah | Not Started | 40 | 60 |  |  |  | UserStory30.py, Main.py |  |  | US30Test .py | US30Test
T39.01 | Write Test Script | dah
T30.02 | Write Method | dah
US12 | Parents not too old | cz | Not Started | 30 | 60 |  |  |  | usrun.py |  |  | usrun_test.py
US19 | First cousins should not marry | cz | Not Started | 50 | 60 |  |  |  | usrun.py |  |  | usrun_test.py
Business Purpose: to implement approximately 25% of then next highest priority validity checks and enhancement features defined for the current release.
Definition of Done: user story is fully implemented and submitted to github along with a corresponding test to prove the functionality of the check/feature.
Business Purpose: to implement approximately 25% of highest priority validity checks and enhancement features defined for the current release.
Definition of Done: user story is fully implemented and submitted to github along with a corresponding test to prove the functionality of the check/feature.
Review Results
Keep doing:
e.g. Bring pizza to our meetings
e.g Bring silverware for everyone
Avoid:
e.g Leaving leftover pizza on the counter

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Stories
Story ID | Story Name | Story Description
US01 | Dates before current date | Dates (birth, marriage, divorce, death) should not be after the current date
US02 | Birth before marriage | Birth should occur before marriage of an individual
US03 | Birth before death | Birth should occur before death of an individual
US04 | Marriage before divorce | Marriage should occur before divorce of spouses, and divorce can only occur after marriage
US05 | Marriage before death | Marriage should occur before death of either spouse
US06 | Divorce before death | Divorce can only occur before death of both spouses
US07 | Less then 150 years old | Death should be less than 150 years after birth for dead people, and current date should be less than 150 years after birth for all living people
US08 | Birth before marriage of parents | Children should be born after marriage of parents (and not more than 9 months after their divorce)
US09 | Birth before death of parents | Child should be born before death of mother and before 9 months after death of father
US10 | Marriage after 14 | Marriage should be at least 14 years after birth of both spouses (parents must be at least 14 years old)
US11 | No bigamy | Marriage should not occur during marriage to another spouse
US12 | Parents not too old | Mother should be less than 60 years older than her children and father should be less than 80 years older than his children
US13 | Siblings spacing | Birth dates of siblings should be more than 8 months apart or less than 2 days apart (twins may be born one day apart, e.g. 11:59 PM and 12:02 AM the following calendar day)
US14 | Multiple births <= 5 | No more than five siblings should be born at the same time
US15 | Fewer than 15 siblings | There should be fewer than 15 siblings in a family
US16 | Male last names | All male members of a family should have the same last name
US17 | No marriages to children | Parents should not marry any of their children
US18 | Siblings should not marry | Siblings should not marry one another
US19 | First cousins should not marry | First cousins should not marry one another
US20 | Aunts and uncles | Aunts and uncles should not marry their nieces or nephews
US21 | Correct gender for role | Husband in family should be male and wife in family should be female
US22 | Unique IDs | All individual IDs should be unique and all family IDs should be unique
US23 | Unique name and birth date | No more than one individual with the same name and birth date should appear in a GEDCOM file
US24 | Unique families by spouses | No more than one family with the same spouses by name and the same marriage date should appear in a GEDCOM file
US25 | Unique first names in families | No more than one child with the same name and birth date should appear in a family
US26 | Corresponding entries | All family roles (spouse, child) specified in an individual record should have corresponding entries in the corresponding family records. Likewise, all individual roles (spouse, child) specified in family records should have corresponding entries in the corresponding individual's records. I.e. the information in the individual and family records should be consistent.
US27 | Include individual ages | Include person's current age when listing individuals
US28 | Order siblings by age | List siblings in families by decreasing age, i.e. oldest siblings first
US29 | List deceased | List all deceased individuals in a GEDCOM file
US30 | List living married | List all living married people in a GEDCOM file
US31 | List living single | List all living people over 30 who have never been married in a GEDCOM file
US32 | List multiple births | List all multiple births in a GEDCOM file
US33 | List orphans | List all orphaned children (both parents dead and child < 18 years old) in a GEDCOM file
US34 | List large age differences | List all couples who were married when the older spouse was more than twice as old as the younger spouse
US35 | List recent births | List all people in a GEDCOM file who were born in the last 30 days
US36 | List recent deaths | List all people in a GEDCOM file who died in the last 30 days
US37 | List recent survivors | List all living spouses and descendants of people in a GEDCOM file who died in the last 30 days
US38 | List upcoming birthdays | List all living people in a GEDCOM file whose birthdays occur in the next 30 days
US39 | List upcoming anniversaries | List all living couples in a GEDCOM file whose marriage anniversaries occur in the next 30 days
US40 | Include input line numbers | List line numbers from GEDCOM source file when reporting errors
US41 | Include partial dates | Accept and use dates without days or without days and months
US42 | Reject illegitimate dates | All dates should be legitimate dates for the months specified (e.g., 2/30/2015 is not legitimate)